## Sheet1
ID | Executable | US | Acceptance Criteria | Points | Sprint
Task1 | Diagrams | As a team, we want to complete our diagrams for visualizing what our project will look like and how it will function | Diagrams are created and approved by the team, clearly showing the project structure and functionality. | 3 | 1
Task2 | Product Backlog | As a team, we want to complete our backlog and plan in what sprint we want to complete each feature | Backlog is fully populated with all features, and each feature is assigned to a specific sprint. | 2 | 1
Task3 | Frontend and Backend Technologies | As a team, we wanted to agree on the technologies we will use to complete our project. | Team agrees on and documents the frontend and backend technologies to be used for the project. | 1 | 1
Task4 | Alogrithms | As a team, we wanted to agree on the algorithms we will use to complete our project. | Team agrees on and documents the algorithms to be used for the project. | 1 | 1
US1 | Account Creation | Given I am someone who wants to create an account, when I try to create an account using SSO then I should be able to create an account that saves my data. | User can successfully create an account using SSO, and their data is saved in the database. | 7 | 1
US2 | User Login | Given I am a user of the application, when I open the application, I should be able to see a username and password field, and then I should be able to use my username and password to login | User can see login fields and successfully log in using their username and password. | 7 | 1
US3 | Home Screen | Given I am a user of the application, when I login, Then I should be able to see the home screen. | User is redirected to the home screen after successful login. | 5 | 1
US4 | Firebase API | Given I am a user with an account, my account data should be stored in a secured database so that there is no risk of data leak. | User data is stored securely in Firebase, and no unauthorized access is possible. | 8 | 2
US5 | Tutor Selection | Given that I am a user of the application, When I login I should be able to see a list of available tutors, and then I should be able to select one that matches my preferences. | User can view a list of tutors and select one based on their preferences. | 10 | 2
US6 | Scheduling API | Given that I am a user of the application, When I select my tutor, I should be able to see available time slots on the calender for that selected tutor. | User can view available time slots for the selected tutor on a calendar. | 9 | 2
US7 | Availability Setting | Given that I am a tutor, when I log in to my profile I want to be able to set my availability for tutoring sessions so that then the students can book time slots | Tutor can set their availability, and students can book sessions based on the tutor's availability. | 8 | 2
US8 | Student Notification | Given that I am a user, I want to recieve reminders for upcoming tutoring sessions so that I do not forget about them | User receives notifications or reminders for upcoming tutoring sessions. | 5 | 2
US9 | Tutor Notification | Given that I am a tutor, I want to receive notifications for tutoring requests so that I can comfirm or decline bookings | Tutor receives notifications for tutoring requests and can confirm or decline them. | 5 | 2
US10 | Schedule Deletion | Given that I am a user , I want to reschedule or cancel tutoring sessions so that i can adjust if my plans change | User can reschedule or cancel tutoring sessions through the app. | 7 | 2
US11 | Schedule Statistics | Given that I am a tutor, I want to track the number of sessions/hours that I have worked and calculate my earnings so that I can manage my schedule and income. | Tutor can view statistics on sessions worked and earnings calculated. | 9 | 3
US12 | Secure Payment | Given that I am a user, I want to make payments for tutoring sessions through the app so that I can book and pay easily. | User can securely make payments for tutoring sessions within the app. | 9 | 3
US13 | Admin Account | Given that I am an admin, I want to have access to all users and session data so that I can manage the platform. | Admin can access and manage all user and session data through the admin panel. | 6 | 3
US14 | Billing Settings | Given that I am a tutor, I want to set my hourly rate so that my students know the cost of my sessions beforehand. | Tutor can set and update their hourly rate, which is visible to students. | 7 | 3
US15 | User Filtering | Given that I am a user, I want to filter my tutors based on subject so that I can choose a tutor who specializes in the content that I need help in | User can filter tutors by subject to find a tutor specializing in the desired content. | 9 | 3
US16 | Schedule Setup | Given that I am a user, I want to book multiple tutoring sessions at once so that I can plan ahead for my tutoring sessions. | User can book multiple tutoring sessions in one go. | 8 | 3
US17 | Group Session Scheduling | Given that I am a user, I want to join group tutoring sessions so that I can learn in a group setting, which will save me money. | User can join group tutoring sessions and see the cost savings compared to individual sessions. | 8 | 3
US18 | Session Note Feature | Given that I am a user, I want to see my session history (Notes of topics covered) so that I can review the topics I have learned. | User can view session history with notes on topics covered. | 7 | 3
US19 | File Sharing | Given that I am a tutor, I want to provide learning resources to students so that they can review/practice outside of the tutoring sessions. | Tutor can upload and share learning resources with students, who can access them outside of sessions. | 7 | 3
As <WHO>, I want/need to <WHAT> so that <WHY>.
WHO for the Role
WHAT for Capability, Task, Hard-goal, and Soft-goal
WHY for Value